## Hoja1
2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 |  | DataProducer 1 | DataProducer 2 | Broker Station | Supervision Station | General | Task | estimated time | Assigned to | Task | estimated time | Assigned to |  | DataProducer 1
2021-11-12: SPRINT 1; 2021-11-13: DP01_lCD deco; 2021-11-26: SPRINT 2 | Task | test on Esp01: LCD Screen | I2C on Esp01 | I2C on MCU Esp8266 | S.S. Wifi connection | connect Esp01 with arduino | Chibi on raspberry | 30 min | Agapito -Edgar | DP01_testFinal.ino | 60 min | Agapito -Edgar | Task | DP01_testFinal.ino
2021-11-14: I2C- arduino test |  | MQTT on DP01 | LCD_display on Esp01 | wifi MCU Esp8266 as A.P. | MQTT_sub | I2C on arduino | I2C chibi-raspberry | 60 min | Agapito | MQTT_Broker_Final.ino | 60 min | Agapito -Edgar |  | MQTT_Broker_Final.ino
2021-11-15: I2C - Esp01 |  | LCD on DP01 (deco) | ADXL345 on Esp01 | MQTT broker | arduino I2C slave | LCD_display on arduino | I2C_arduino as Slave - raspberry as master | 90 min | Agapito | DP02_Final.ino | 60 min | Agapito -Edgar |  | DP02_Final.ino
2021-11-15: I2C - Esp8266MCU |  | DP01-MQTT_pub | DP02-MQTT_pub | Mpc23017 I2C |  | ADXL345 on arduino | UART chibi-raspberry /lcd Screen | 60 min | Agapito -Edgar |  |  |  |  | supervision_Station-Final
2021-11-16: MCP23017 -search |  | DP01_Final.ino | DP02_wifi as sta | led implementation |  | Mosquitto | Supervition_Station-Wifi-MQTT | 15 min | Agapito -Edgar
2021-11-16: MCP23017 -I2C-implementation |  |  | DP02_Final.ino | BrokerStation_ final.ino |  | MQTT_Sub_Pub | LCD_Sup.Station deco(chibi-raspberry) | 90 min | Agapito -Edgar
2021-11-18: MQTT_broker_Station build | [5 empty] | MQTT - Topic | I2C_Arduino | 60 min | Agapito
2021-11-20: MQTT-BROKER | [6 empty] | supervision_Station-Final | 30 min | Agapito -Edgar
| mosquitto test |  |  |  |  | Mosquitto as sub tester
ADXL345-I2C-Arduino
ADXL345-I2C-Esp01
LCDdisplay-I2C-Esp01
DP01-MQTT_pub
DP02-MQTT_pub
Esp01-Arduino
Supervision_Station-MQTT_sub